## Sheet1
AI SMART MIRROR USING RASPBERRY PI 3B+
Daily Log Book
Date | Day | Record Main Activities | Timings
2023-02-27 | Monday | Attended team meeting to discuss project goals for the week. | 10:00 to 01:25
2023-02-28 | Tuesday | Researched potential project topics and narrowed down list. | 10:00 to 01:26
2023-03-01 | Wednesday | Developed project Scope document and submitted to supervisor for feedback. | 10:00 to 01:27
2023-03-02 | Thursday | Revised project proposal based on feedback from supervisor.
2023-03-03 | Friday | Finalized project proposal and submitted to supervisor for approval.
2023-03-25 | Saturday | REPORT DAY
2023-03-05 | Sunday | Holiday
2023-03-06 | Monday | Today we started our project, AI Smart Mirror Using Raspberry Pi 3B+. Our first task was to define the project scope and objectives. We identified the user and their needs, and conducted market research on existing smart mirror products. We established project goals and objectives, which we recorded in our project charter.
2023-03-07 | Tuesday | We continued working on our project charter and created a project plan.
2023-03-08 | Wednesday | We defined the project scope and deliverables, and developed a project timeline and budget.
2023-03-09 | Thursday | Today we assigned project team roles and responsibilities. We also identified project risks and created a mitigation plan
2023-03-10 | Friday | We reviewed and finalized our project charter and project plan.
2023-03-25 | Saturday | REPORT DAY
2023-03-05 | Sunday | Holiday
2023-03-13 | Monday | We reviewed the feedback from our instructor and made necessary revisions to our project charter and project plan.
2023-03-14 | Tuesday | Began researching and selecting hardware components for our smart mirror.
2023-03-15 | Wednesday | We continued researching and selecting hardware components, taking into consideration the cost and functionality of each component. We also ordered some of the hardware components we needed.
2023-03-16 | Thursday | We continued ordering the hardware components we needed for our smart mirror. We also discussed how we would integrate the hardware components.
2023-03-17 | Friday | We reviewed our progress so far and discussed any potential issues. We also began designing the hardware components for our smart mirror.
2023-03-25 | Saturday | REPORT DAY
2023-03-05 | Sunday | Holiday
2023-03-20 | Monday | researched different materials that we could use to build the frame for our smart mirror.
2023-03-21 | Tuesday | We also began designing the software components for our smart mirror.
2023-03-22 | Wednesday | reviewed our progress so far and discussed any issues that we encountered.
2023-03-23 | Thursday | continued designing the software components for our smart mirror, focusing on the artificial intelligence aspect of the mirror.
2023-03-24 | Friday | we tested some of the hardware and software components and began integrating them. also reviewed our project timeline and budget to ensure that we were still on track.
2023-03-25 | Saturday | REPORT DAY
2023-03-05 | Sunday | Holiday
2023-03-27 | Monday
2023-03-28 | Tuesday
2023-03-29 | Wednesday
2023-03-30 | Thursday
2023-03-31 | Friday
2023-04-01 | Saturday
2023-04-02 | Sunday
2023-04-03 | Monday
2023-04-04 | Tuesday
2023-04-05 | Wednesday
2023-04-06 | Thursday
2023-04-07 | Friday
2023-04-08 | Saturday
2023-04-09 | Sunday
2023-04-10 | Monday
2023-04-11 | Tuesday
2023-04-12 | Wednesday
2023-04-13 | Thursday
2023-04-14 | Friday
2023-04-15 | Saturday
2023-04-16 | Sunday
2023-04-17 | Monday
2023-04-18 | Tuesday
2023-04-19 | Wednesday
2023-04-20 | Thursday
2023-04-21 | Friday
2023-04-22 | Saturday
2023-04-23 | Sunday
2023-04-24 | Monday
2023-04-25 | Tuesday
2023-04-26 | Wednesday
2023-04-27 | Thursday
2023-04-28 | Friday
2023-04-29 | Saturday
2023-04-30 | Sunday
2023-05-01 | Monday
2023-05-02 | Tuesday
2023-05-03 | Wednesday
2023-05-04 | Thursday
2023-05-05 | Friday
2023-05-06 | Saturday
2023-05-07 | Sunday
2023-05-08 | Monday
2023-05-09 | Tuesday
2023-05-10 | Wednesday
2023-05-11 | Thursday
2023-05-12 | Friday
2023-05-13 | Saturday
2023-05-14 | Sunday